Event Photo Database

Azure Migration: Development & Deployment Plan, Effort, and Cost Comparison

Prepared for IT, Youth4AM / mmrunners  |  June 18, 2026  |  Companion file: Azure_vs_GCP_Cost_Model.xlsx

# 1. Executive summary

The cloud-webapp is being built for Google Cloud: a React front end on Firebase Hosting, a Node/Express API and a Python face-matcher on Cloud Run, a Python indexer as a Cloud Run Job, Firestore as the database, Cloud Storage for photos, Firebase Auth, Secret Manager, and GitHub Actions deploys. The same shape runs cleanly on Azure: every component has a near-equivalent, and because the app is already containerised the compute layers move with little code change. The real work is swapping the four managed-service SDKs (Firestore, Cloud Storage, Firebase Auth, Secret Manager) and rebuilding the deploy pipeline.

Effort: roughly 50-75 developer-days (about 10-15 weeks part-time for one engineer who knows the codebase), dominated by the database and auth swaps. Cost: at this org's scale both clouds bill well under $10/month at list price and effectively $0 while the nonprofit grant lasts. Staying under $100/month is comfortable - the new Azure workload adds about $1-7/month, so even on top of the existing $65/month you land near $66-72/month, and the $2,000/year grant covers the new workload many times over.

Recommended scope (you asked us to decide): move compute, storage, database, auth, secrets, CI/CD and schedulers to Azure, but keep Google Workspace / Shared Drive as the photo source and keep Google Drive ingestion in the indexer. Drive is free under the org's Workspace plan, the indexer already refreshes Drive tokens, and re-platforming the Drive integration would add cost and risk for no benefit. This is a 'compute + storage + data' migration, not a Workspace migration.

# 2. What is being ported (current GCP architecture)

The cloud-webapp monorepo has five deployable pieces plus supporting infrastructure:

| Component | Today (GCP) | Role |
| --- | --- | --- |
| web | Firebase Hosting (Vite + React 18 + TS static build) | Front end served at photos.mmrunners.org; /api/** rewrites to Cloud Run |
| api | Cloud Run (Node 20, Express 4) | Auth, Firestore CRUD, signed-URL photo serving, Drive calls, triggers indexer |
| matcher | Cloud Run (Python, Flask + gunicorn) | Loads ONNX models, in-memory cosine similarity over face vectors |
| indexer | Cloud Run Job (Python) | Per-event batch: pulls photos from Drive, embeds faces (onnxruntime/opencv), writes .npy vectors + Firestore |
| data + infra | Firestore, Cloud Storage, Firebase Auth, Secret Manager, Artifact Registry, Cloud Scheduler, Cloud Logging | State, secrets, images, identity, scheduling, observability |

Key SDK dependencies that must change: @google-cloud/firestore, @google-cloud/storage, firebase-admin (token verification) in the Node API; google-cloud-storage and google-cloud-firestore in the Python indexer; google-cloud-storage in the matcher. The googleapis Drive client and the onnxruntime/opencv model code stay as-is.

# 3. GCP-to-Azure service mapping

| GCP service | Azure equivalent | Migration note |
| --- | --- | --- |
| Firebase Hosting | Azure Static Web Apps (Free) | Free TLS + custom domain + CDN; built-in /api proxy to Container Apps |
| Cloud Run (api, matcher) | Azure Container Apps (Consumption) | Same container, scales to zero, same free-grant model; redeploy the image |
| Cloud Run Job (indexer) | Azure Container Apps Job | Manual/event/cron-triggered job; same image |
| Firestore | Azure Cosmos DB for NoSQL | Closest document model; biggest semantic gap (queries, indexes, security rules) |
| Firebase Auth | Microsoft Entra External ID | Free under 50k MAU; swap client SDK (MSAL) and server token validation |
| Cloud Storage + signed URLs | Azure Blob Storage + SAS tokens | Container per bucket; signed URL -> SAS; copy data with azcopy |
| Cloud CDN | Static Web Apps CDN (avoid Front Door) | Front Door Standard has a ~$35/mo base fee - not needed at this scale |
| Secret Manager | Azure Key Vault | References injected as Container Apps secrets |
| Artifact Registry | Azure Container Registry (Basic) or GitHub CR | GHCR is free; ACR Basic is ~$5/mo |
| Cloud Scheduler | Container Apps Job cron / Logic Apps | For the index-scan and sync schedulers |
| Cloud Logging / Error Reporting | Azure Monitor + Application Insights | pino JSON logs still work; add App Insights SDK |
| GitHub Actions + Workload Identity Fed. | GitHub Actions + Azure OIDC federation | Same keyless pattern; az login with federated credentials |

# 4. Development effort by component

Estimates are developer-days for one engineer familiar with the codebase. Ranges reflect the usual unknowns (data-shape surprises, auth edge cases). 'Risk' flags where estimates could grow.

| Workstream | Low (d) | High (d) | What the work is / risk |
| --- | --- | --- | --- |
| Front end -> Static Web Apps | 2 | 3 | Hosting is config + DNS; real work is swapping Firebase Auth client SDK for MSAL/Entra |
| API -> Container Apps | 8 | 12 | Swap Firestore, Storage, firebase-admin, Secret Manager SDKs; container already exists. Risk: medium |
| Database Firestore -> Cosmos DB | 6 | 10 | Query + index rewrites, move Firestore security-rules logic into the API, data export/import. Risk: HIGH |
| Auth -> Entra External ID | 4 | 6 | Tenant + user flows, migrate/re-invite ~50 admins, server JWT validation. Risk: medium |
| Photo storage -> Blob + SAS | 3 | 5 | Container layout, SAS signing, azcopy bulk transfer of ~100 GB, lifecycle tiering |
| Matcher -> Container Apps | 3 | 4 | Storage client swap only; ONNX/cosine code unchanged; models load from Blob |
| Indexer -> Container Apps Job | 4 | 6 | Storage + DB client swap; keep Drive token refresh; onnxruntime image unchanged |
| Secrets -> Key Vault | 1 | 1 | Mechanical |
| Schedulers | 1 | 2 | Recreate index-scan + sync schedules as Job cron / Logic Apps |
| CI/CD + infra bootstrap (Bicep/az) | 6 | 9 | Rewrite 3 deploy workflows + bootstrap script; OIDC federation; ACR/GHCR build-push |
| Observability | 1 | 2 | App Insights wiring + dashboards |
| Parity testing, cutover, DNS, docs | 5 | 8 | Dual-run, smoke tests, DNS flip, runbook updates |

|  | Low | High |
| --- | --- | --- |
| Total developer-days | 44 | 68 |
| + 15% integration/PM overhead | ~50 | ~78 |
| Calendar (one engineer, part-time) | ~10 wks | ~15 wks |

Single biggest risk: Firestore has no Cosmos equivalent for its declarative security rules (infra/firestore.rules). Every access check those rules enforce today must be re-implemented in the API's requireAuth/requireAdmin middleware before cutover. Scope this first - it is the item most likely to expand the estimate.

# 5. Phased development & deployment plan

## Phase 0 - Decisions & grant (week 0, ~2 days)

- Confirm the $2,000 Azure nonprofit grant is active; note it does not roll over and renews annually.

- Confirm what the current $65/month actually is (see Section 7) - it changes the budget math.

- Decide data model: Cosmos serverless vs provisioned free tier (recommend the free tier - see cost model).

- Lock the scope: keep Google Drive as photo source + Drive ingestion; everything else moves.

## Phase 1 - Landing zone & CI/CD (week 1-2, ~7 days)

- Create resource group, Container Apps (Consumption) environment, Cosmos account (free tier), Storage account (LRS), Key Vault, Static Web App, Entra External ID tenant.

- Write Bicep (or az CLI) bootstrap to replace bootstrap-gcp.sh; set up GitHub OIDC federated credentials (no stored secrets).

- Set guardrails on day one: $80/mo budget alert, cost-anomaly alert, Log Analytics 5 GB daily cap, Container Apps max-replicas caps.

## Phase 2 - Data & storage (week 2-4, ~12 days)

- Model Firestore collections (events, clubs, photos, upload-links, audit-log) as Cosmos containers; define partition keys + indexes.

- Re-implement firestore.rules access logic inside API middleware.

- azcopy the ~100 GB photo library GCS -> Blob; set Cool tier on originals, Hot on derivatives, lifecycle rule at 30 days.

- Build a one-shot Firestore -> Cosmos export/import; validate counts and a sample of documents.

## Phase 3 - Services (week 4-7, ~18 days)

- API: replace @google-cloud/firestore -> @azure/cosmos, @google-cloud/storage -> @azure/storage-blob (SAS), firebase-admin -> Entra JWT validation, Secret Manager -> Key Vault references. Deploy to Container Apps.

- Matcher: swap storage client, load models from Blob, deploy to Container Apps.

- Indexer: swap storage + DB clients, keep Drive token refresh, deploy as a Container Apps Job; recreate schedulers.

- Front end: swap Firebase Auth SDK for MSAL/Entra; deploy to Static Web Apps with /api proxy to the API.

## Phase 4 - Parity, cutover, decommission (week 7-10+, ~13 days)

- Dual-run: keep GCP live, run Azure in parallel; mirror writes for ~1 week to catch parity bugs.

- Smoke-test every route; verify auth, photo serving, indexing, matching end-to-end.

- Flip DNS for photos.mmrunners.org to the Static Web App; monitor egress + errors for 48h.

- Decommission GCP services once stable; keep a cold backup for 30 days.

# 6. Cost comparison: GCP vs Azure

Sized for this org: ~50 admin users, ~10k DB reads/day, ~100 GB photos, ~50 GB/mo photo egress, light request volume. Figures are list price (no credit); the full model with formulas is in Azure_vs_GCP_Cost_Model.xlsx.

| Layer | GCP $/mo | Azure $/mo | Note |
| --- | --- | --- | --- |
| Hosting + compute (web, api, matcher, indexer) | $0 | $0 | Inside both clouds' always-free monthly grant |
| Database | $0.48 | $0.61 | Firestore vs Cosmos serverless; ~$0 on Cosmos free tier |
| Photo storage (100 GB) | $2.00 | $1.80 | GCS Standard vs Blob Hot LRS |
| Photo egress (50 GB) | $6.00 | $0.00 | Azure's first 100 GB/mo free; GCP $0.12/GB |
| Secrets + registry + misc | $0.16 | $5.05 | ACR Basic $5 (or $0 via GitHub CR) |
| TOTAL (list, no credit) | $8.64 | $7.46 | Both trivial; egress dominates GCP |
| TOTAL (with nonprofit grant) | $0 | $0 | GCP grant $10k/yr; Azure grant $2k/yr |

Read-out: at this scale the two clouds cost about the same at list price (~$7-9/month), and Azure is actually slightly cheaper on storage and egress. The headline difference is the grant size - GCP's $10,000/year vs Azure's $2,000/year - but $2,000/year is still ~$167/month, roughly 20x the list spend, so the smaller grant is irrelevant at this workload. The decision should rest on team familiarity and the existing $65/month Azure footprint, not raw price.

# 7. Keeping the monthly bill under $100

The math. Ceiling $100 - existing $65 = $35/month of headroom for the new workload. The recommended cheapest Azure config adds about $1/month at list price (Blob storage + a few cents of Key Vault), so total cash lands near $66/month - comfortably under $100 - and the $2,000/year grant covers the new workload for, in practice, indefinitely at this scale.

Important caveat about the $65. The Azure nonprofit grant only offsets Azure consumption. If the existing $65/month is a Microsoft 365 / Business Premium licence cost, the grant will NOT reduce it - but it also won't grow, and the new workload still rides the grant to ~$0, so you stay near $65-66/month. If the $65 is already Azure consumption, the grant absorbs both it and the new workload. Either way you remain under $100; confirm which it is so the forecast is exact.

## Levers that keep it there

- Use the $2,000/year grant - it is ~$167/month, far above the ~$7/month list spend. The real job is staying under the grant so there is no cash bill at all.

- Do NOT provision Azure Front Door Standard (~$35/month base). Use Static Web Apps' built-in CDN; serve photos via Blob SAS URLs with cache headers.

- Container Apps: Consumption environment only, min-replicas = 0 (scale to zero), max-replicas capped. Avoid Dedicated workload profiles, which bill hourly even when idle.

- Cosmos DB: use the provisioned free tier (1,000 RU/s + 25 GB free, one per subscription) rather than serverless - it makes the database line $0 at this volume.

- Blob: originals in Cool/Cold tier, derivatives in Hot, lifecycle rule to demote after 30 days; LRS not GRS; never serve full-resolution originals to the browser.

- Container registry: push images to GitHub Container Registry (free) and pull into Container Apps to avoid the ~$5/month ACR Basic fee.

- Guardrails: $80/month budget alert with 50/80/100% thresholds, cost-anomaly alerts (egress is the classic surprise), and a 5 GB Log Analytics daily cap.

Bottom line: under $100/month is not tight - it is the default outcome. The only line that can blow the budget is uncached full-resolution photo egress, which the SAS + CDN + cache-header pattern (already the design intent on GCP) prevents.

# 8. Pricing sources

Azure Container Apps pricing: https://azure.microsoft.com/en-us/pricing/details/container-apps/

Azure Cosmos DB serverless pricing: https://azure.microsoft.com/en-us/pricing/details/cosmos-db/serverless/

Azure Cosmos DB lifetime free tier: https://learn.microsoft.com/en-us/azure/cosmos-db/free-tier

Azure Blob Storage pricing: https://azure.microsoft.com/en-us/pricing/details/storage/blobs/

Azure bandwidth / egress pricing: https://azure.microsoft.com/en-us/pricing/details/bandwidth/

Azure Static Web Apps pricing: https://azure.microsoft.com/en-us/pricing/details/app-service/static/

Microsoft Entra External ID pricing: https://azure.microsoft.com/en-us/pricing/details/microsoft-entra-external-id/

Microsoft for Nonprofits - Azure grant: https://learn.microsoft.com/en-us/industry/nonprofit/microsoft-for-nonprofits/claim-activate-nonprofit-azure-grant